Assignment -2

Que. 1 What is an Agile Development Model? Why is Agile preferred when requirements are expected to change frequently?

Que. 2 Explain the following Agile models/methodologies:

- Scrum

- Extreme Programming (XP)

- Feature Driven Development (FDD)

- Crystal

- Kanban

- Adaptive Software Development (ASD)

- Test Driven Development (TDD)

Que. 3 Which model would you recommend for a startup developing an AI-based mobile application with frequently changing customer requirements? Justify your answer.

Que. 4 Consider a project:

"College Management System" that manages student admission, attendance, examination, fees and faculty information.

Identify:

- Product Owner

- Scrum Master

- Development Team

- Students

- Faculty

- College Management

- System Administrator

Que. 5 Differentiate between cycle time and lead time with a simple example.

Que. 6 What are the three roles defined in Scrum? Briefly describe each.

Que. 7 List any four practices of Extreme Programming (XP).

Que. 8 Compare and contrast Kanban and Scrum based on:

- Roles and responsibilities

- Artifacts

- Cadence and ceremonies

- Suitability for different project types

Que. 9 What is Requirements Elicitation in Agile? Discuss at least five elicitation techniques used in Agile projects (e.g., interviews, workshops, prototyping, observation, user story mapping)

Que. 10 Calculate Velocity and Sprint Burndown for the following data and plot the ideal burndown vs. actual burndown. What does this chart indicate about team performance?

| Day | Remaining Story Points |
| --- | --- |
| Day 0 (Start) | 40 |
| Day 1 | 38 |
| Day 2 | 35 |
| Day 3 | 30 |
| Day 4 | 28 |
| Day 5 | 22 |
| Day 6 | 20 |
| Day 7 | 15 |
| Day 8 | 12 |
| Day 9 | 8 |
| Day 10 (End) | 5 |

Que. 11 A company is developing an AI-powered recommendation system for an e-commerce website.

Initially, the customer requested only:

"Recommend products based on previous purchases."

After two sprints, the customer requested:

"The system should also consider browsing history, current trends and customer location."

Answer the following:

- How would a traditional Waterfall approach handle this change?

- How would an Agile team handle it?

- Which Agile benefits are demonstrated?

- Which Agile practices can help manage this change?

- What could happen if the team refuses to accept the change?

Que. 12 Explain Agile Design Principles with examples

Que. 13 Why is refactoring important in Agile?

Que. 14 What is a Daily Stand-up (Daily Scrum)? What are the three questions each member answers?

Que. 15 Create a comparison table for Sprint Review vs. Sprint Retrospective covering below points:

- Purpose and focus

- Participants

- Outputs/artifacts

- Frequency and duration

- Who drives the meeting